## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the Milestone Description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use Progress to add how much of the project you finished by adding a percentage number. • Add the day you started your project in the Start Date. • Finish your calculations by filling in the number of days you need to complete your project in the No. of Days field.

## Light
PROJECT TITLE
Company name |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2021-11-12 |  |  |  |  | November | [20 empty] | December | [27 empty] | January
Scrolling Increment: | 1 | time axis 2021-11-13 to 2022-01-07
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2021-11-13 to 2022-01-07
TITLE 1
Task 1 | Goal | Name | 25% | 2021-11-12 | 3 | 2021-11-13: 2; 2021-11-14: 2
Task 2 | Milestone |  |  | 2021-11-17 | 1 | bar: 2021-11-17
Task 3 | Low Risk |  | 50% | 2021-11-09 | 10
Task 4 | Milestone |  |  | 2021-12-02 | 1 | bar: 2021-12-02
Task 5 | Med Risk |  | 10% | 2021-11-18 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2021-11-18 | 13
Task 2 | On Track |  | 50% | 2021-11-20 | 9
Task 3 | Low Risk |  | 33% | 2021-11-25 | 11
Task 4 | Milestone |  |  | 2021-11-27 | 1 | bar: 2021-11-27
Task 5 |  |  |  | 2021-11-28 | 24
TITLE 3
Task 1 | On Track |  |  | 2021-11-27 | 4
Task 2 | Med Risk |  |  | 2021-11-30 | 14
Task 3 | On Track |  |  | 2021-12-15 | 6
Task 4 | Goal |  |  | 2021-12-19 | 3 | 2021-12-19: 2; 2021-12-20: 2; 2021-12-21: 2
Task 5 | Low Risk |  |  | 2021-11-18 | 19
TITLE 4
Task 1 |  |  |  | 2021-12-22 | 15
Task 2 |  |  |  | 2022-01-05 | 5
Task 3 | Milestone |  |  | 2022-02-16 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one

## Dark
PROJECT TITLE
Company name |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2021-11-12 |  |  |  |  | November | [20 empty] | December | [27 empty] | January
Scrolling Increment: | 1 | time axis 2021-11-13 to 2022-01-07
Milestone description | Category | Assigned to | Progress | Start | Days | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F
TITLE 1
Task 1 | Goal | Name | 25% | 2021-11-12 | 3 | S: 2; S: 2
Task 2 | Milestone |  |  | 2021-11-17 | 1 | bar: W
Task 3 | Low Risk |  | 50% | 2021-11-09 | 10
Task 4 | Milestone |  |  | 2021-12-02 | 1 | bar: T
Task 5 | Med Risk |  | 10% | 2021-11-18 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2021-11-18 | 13
Task 2 | On Track |  | 50% | 2021-11-20 | 9
Task 3 | Low Risk |  | 33% | 2021-11-25 | 11
Task 4 | Milestone |  |  | 2021-11-27 | 1 | bar: S
Task 5 |  |  |  | 2021-11-28 | 24
TITLE 3
Task 1 | On Track |  |  | 2021-11-27 | 4
Task 2 | Med Risk |  |  | 2021-11-30 | 14
Task 3 | On Track |  |  | 2021-12-15 | 6
Task 4 | Goal |  |  | 2021-12-19 | 3 | S: 2; M: 2; T: 2
Task 5 | Low Risk |  |  | 2021-11-18 | 19
TITLE 4
Task 1 |  |  |  | 2021-12-22 | 15
Task 2 |  |  |  | 2022-01-05 | 5
Task 3 | Milestone |  |  | 2022-02-16 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one

## Color
PROJECT TITLE
Group 19 |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead | Victoria | Carl | Anna | Katherine
Project Start Date: | 2021-09-14 |  |  |  |  | September | [20 empty] | October | [27 empty] | November
Scrolling Increment: | 0 | time axis 2021-09-14 to 2021-11-08
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2021-09-14 to 2021-11-08
Iteration 1
Iteration planning and meeting | Goal | Katherine | 75% | 2021-09-14 | 1 | 2021-09-14: 2
Complete stakeholder register | High Risk | Carl Victoria | 100% | 2021-09-15 | 5
Design persona | Low Risk | Anna | 50% | 2021-09-20 | 5
Review and test persona | Med Risk | Carl | 75% | 2021-09-24 | 5
Complete progress report | On Track | Victoria | 100% | 2021-09-28 | 3
Milestone 01 | Milestone |  | 10% | 2021-10-01 | 1 | bar: 2021-10-01
Iteration 2
Iteration planning and meeting | Goal | Anna | 50% | 2021-10-14 | 2 | 2021-10-14: 2; 2021-10-15: 2
Complete Grantt chart | Med Risk | Cral | 90% | 2021-10-16 | 5
Complete requirement list | High Risk | Victoria | 90% | 2021-10-20 | 5
Assign the tasks identified in the Grantt chart | Low Risk | Katherine | 75% | 2021-10-23 | 3
Complete progress report | On Track | Victoria | 100% | 2021-10-26 | 1
Milestone 02 | Milestone |  | 50% | 2021-10-27 | 1 | bar: 2021-10-27
Iteration 3
Iteration planning and meeting | Goal | Carl | 75% | 2021-10-29 | 1 | 2021-10-29: 2
Complete risk register | Med Risk | Victoria | 90% | 2021-10-30 | 5
Group members push the files to GitHub | High Risk | All | 100% | 2021-11-04 | 3
Check the Iteration and publish | Med Risk | Katherine | 60% | 2021-11-07 | 3
Complete the user acceptance test results template | High Risk | Carl Victoria | 90% | 2021-11-09 | 2
Complete progress report | On Track | Anna | 100% | 2021-11-10 | 1
Milestone 03 | Milestone |  | 90% | 2021-11-11 | 1
TITLE 4
Task 1 |  |  |  | 2021-11-10 | 15
Task 2 |  |  |  | 2021-11-24 | 5
Task 3 | Milestone |  |  | 2022-01-05 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one
Formulas:
Katherine = [Katherine, row above]+14